### Minutes/Conclusions of the introductory NIL visits in Trondheim (November 24-27, 2009) and Bratislava (November 30 – December 1, 2009)

Due to the late start of the project visits NO->SK planned to the int. conference Virtual University in December 2009 have to be reallocated to the Int. Conference Cybernetics and Informatics in February 2009. It is necessary to ask for the transfer of the non-spent finances to the next year.

Huba, Zakova, December 20, 2009

To publish topics of possible Diploma thesis for MSc. Student mobilities SK->NO and NO->SK.

All partners, December 5, 2009

To prepare proposals for organization of the workshop/summer school in 2009, especially with respect to

- appropriate date (originally planned in September 2009),

- lecturers (professors, or also PhD students and assistants?),

- character of lectures (theoretical, practical tasks with experiments & computers, combination of both),

- contributions to Workshop Preprints (300 pages, 100 pcs.),

- possible extension – combination with other projects and support schemes (Socrates-Erasmus, etc.).

All partners, January 31, 2009

To prepare proposal for character and structure + preliminary titles & abstracts of proposed contributions of the planned joint development of teaching materials on advanced control “Selected Topics of Robust, Constrained and Nonlinear Control” including e.g. model predictive control, optimization, constrained and nonlinear control, PID control, Internet based learning and experimenting, computer simulations and different control applications (Textbook, 300 pages, 100 pcs.+Workbook, 300 pages, 100 pcs.).

All partners, January 31, 2009

Conclusions to both above points (workshop & teaching materials) should be taken at the next coordinating meeting in the middle of February in Slovakia.

All partners, February, 2009

To establish project web page.

Huba, Zakova, December 20, 2009

To prepare proposals of conference and journal papers declaring project support (15 for the total project duration) – there are welcomed joint publications.

All partners, continuously.

To ask for reallocation of one PhD mobility NO->SK from 1Q 2011 to 1Q 2010.

Huba, Zakova, December 20, 2009